MERGE LAB

Build Audit and Work Split

A pre-push interface contract registry for teams whose members code with AI agents

Prepared for: the Merge Lab team   Event: First Commit, Bharat Builds Tour (AWS Builder Center)   Date: 20 September 2026

Codebase: 10 packages, 95 tests, all typecheck clean   Track: Ship It (Best UI as a second target)

# 1. Where the project stands

Every package the demo needs is built and tested. The reasoning-heavy engineering is finished: AST-based extraction with cross-file type resolution, six deterministic drift rules, a CLI that reads uncommitted work, and both agent hook entrypoints with the real deny contract. Roughly 95% of the demo-critical scope exists in code.

The risk has moved entirely out of the codebase. Nothing has ever executed on AWS, no demo repository exists, the two-run experiment has never been rehearsed, and the three-minute video has not been recorded. A judge scoring the project today would see a passing test suite and nothing else, because every visible element of the product sits behind a deployment that has not happened and a recording that does not exist.

The single most important sentence in this document: adding more features will not raise the score. Finishing the deployment, the rehearsal and the video is the only remaining work that changes the outcome.

# 2. What is built

| Package | What it does | State | Tests |
| --- | --- | --- | --- |
| packages/shared | Zod schemas as source of truth, inferred types, shapeHash, functional dependency classes, all API request and response schemas | Complete | 6 |
| packages/extractor | ts-morph extraction of signatures, shapes, deps, routes and env names; cross-file shape inlining; redactor; fail-to-empty counter | Complete | 21 |
| services/resolver | Six deterministic drift rules, version and supersession logic, board assembly, scenarios table | Complete | 17 |
| services/ingest, context, verdict, board | The four Lambda handlers behind one HTTP API | Written, never deployed | 17 |
| infra/template.yaml | SAM stack: ap-south-1, Node 20, ARM64, one DynamoDB table plus GSI1, five functions | Written, never deployed | n/a |
| packages/daemon | CLI publisher: publish, context, check, init; identity, git change detection, context rendering | Complete | 18 |
| packages/hooks | Claude Code SessionStart and PreToolUse; warn/block modes; 300 ms budget; fails open | Complete | 14 |
| board/ | Projector-legible UI: branches, contracts, drift feed; 3 s poll; light and dark; demo mode | Complete | n/a |

### Core requirements satisfied

- Working-tree observation including uncommitted and untracked files

- Declaration extraction with cross-file shape resolution

- Contract registry with versioning and supersession

- Context injection into a starting agent session, phrased as factual statements

- All six drift rules, deterministic, with linter-style reason strings

- Enforcement: a pending write that drifts is denied with a reason the agent can act on

- Team board with explicit "not reporting" labelling so absence never reads as evidence

### Cut on purpose, and staying cut

Each of the following was dropped for the same reason: it does not appear in a three-minute video. Filesystem watcher (replaced by a CLI), Codex and Antigravity adapters, the Bedrock semantic tier, the coupling graph, session summarisation, Slack and PR ingestion, claim-and-release, override learning, multi-language extractors, the IDE surface, Cognito, EventBridge, the notify Lambda and the offline queue.

If asked in judging: say these were scoped out deliberately and name the reason. A deliberate cut is engineering judgement; an unexplained gap is an oversight.

# 3. What is left

| # | Item | Code? | Owner | Est. |
| --- | --- | --- | --- | --- |
| 1 | Deploy the SAM stack and pass the smoke test | No | Aryan | 0.5–4 h |
| 2 | Prove the four-hop spine end to end against the real API | No | Aryan | 1 h |
| 3 | Build the demo repository with two branches and seeded drift | No | Person A | 1 h |
| 4 | Rehearse the two-run experiment until it works twice consecutively | No | Person A | 1–2 h |
| 5 | Capture raw screen footage of both runs | No | Person A | 1 h |
| 6 | README and architecture diagram | Part | Person A | 1 h |
| 7 | Landing page and Merge Lab rename | Yes | Person B | 3–4 h |
| 8 | Edit and narrate the three-minute video | No | Person B | 2–3 h |
| 9 | Builder Center blog post | No | Person B | 1 h |
| 10 | Submission checklist and verification | No | Person B | 0.5 h |

Critical path: items 1 and 2 block items 4, 5 and 8. Items 3, 6, 7 and 9 are not blocked by anything and should start immediately, in parallel, regardless of how the deployment is going.

# 4. Person A — Demo and Proof

You own everything that turns working code into visible evidence. Your output is raw footage and a repository a stranger can read. Nothing you build here ships to production, and that is fine — the demo is the product as far as the judges are concerned.

### A1. Demo repository

Create a scratch repository, separate from the Merge Lab codebase, that stands in for a team’s project. Merge Lab watches it; the two branches represent two developers.

- Repository name: demo-orders. Initialise it, commit an empty scaffold, then branch.

- Branch feat/user-api, owner "dev-a": express plus axios, a User type with snake_case fields (user_id, full_name, created_at), a getUser function, a POST /api/users route, and a DATABASE_URL environment reference.

- Branch feat/profile-ui, owner "dev-b": the consumer of getUser.

- Lift the shapes directly from fixtures/repo-a and fixtures/repo-b in the main repository. They are already the exact form the drift rules expect, so do not invent new ones.

- Leave the work uncommitted on both branches. This is the entire point of the product and must be visible on camera.

### A2. Rehearse the two-run experiment

The demo is not a feature tour. It is the same task run twice with one variable changed.

Run 1 — Merge Lab off

- Dev A’s agent builds the endpoint: installs axios, defines getUser returning user_id and full_name. Nothing is committed or pushed.

- Dev B’s agent is given the dependent task with no shared context.

- Dev B picks node-fetch and writes userId.

- The merge compiles and returns undefined.

Run 2 — Merge Lab on

- Dev A works; the board updates live with the new dependency, signature and owner.

- Dev B starts a fresh session. The injected context block is visible in the transcript on screen.

- Dev B writes user_id and reuses axios without being told.

- Dev B’s agent then attempts a fetch call; the pre-write hook denies it with a one-line reason and the agent self-corrects with no human input in frame.

- The merge is mechanical.

Acceptance: both runs complete twice in a row without improvisation. If it only works once, it will fail on camera.

### A3. Capture the footage

- Record at 1080p or higher, terminal font size large enough to read at projector distance.

- Two terminals side by side, plus the board visible in a browser.

- Capture Run 2 first and in full — it is the primary footage. Then Run 1 as the contrast.

- Get a clean, uninterrupted take of the moment the hook denies the write. That is the single most important four seconds of the submission.

- Hand the raw files to Person B. Do not edit them yourself.

### A4. README and architecture diagram

- Root README: what the problem is in two sentences, the architecture diagram, a one-command local setup, and how to run the scenarios table.

- Architecture diagram: developer machines, the AWS control plane, and the board. Name every service. Keep it line-art and legible when scaled down.

- State plainly that authentication is a single static workspace token today. Do not imply otherwise.

- Include the "not yet built" list from infra/README.md so the seams are visible and deliberate.

# 5. Person B — Story and Surface

You own everything a judge actually looks at. The video is the entire judging surface — there is no live demo — so it outweighs every other deliverable in this document, including the landing page. If you run short of time, cut the landing page, not the video.

### B1. The three-minute video

| Time | Content |
| --- | --- |
| 0:00–0:20 | The problem, first person and specific: forty minutes lost waiting for a teammate to push — not for their code, but for three facts about it. The same thing happened during an LFX mentorship. |
| 0:20–0:35 | What Merge Lab is, in one sentence: a linter for your teammates’ unpushed decisions. |
| 0:35–1:20 | Run 2 on screen: dev A declares, the board updates, dev B’s agent starts already knowing, dev B writes matching code. |
| 1:20–1:50 | The block: the agent attempts fetch, is denied with a reason, and self-corrects. No human input in frame. |
| 1:50–2:10 | Run 1 replayed fast: same prompts, no Merge Lab, the undefined at the end. |
| 2:10–2:45 | Architecture: the diagram, services named, one honest sentence on why serverless and why enforcement is deterministic. |
| 2:45–3:00 | What we learned, concretely: hook payload differences across agent runtimes, the factual-phrasing constraint on injected context, and cold start as the real latency budget. |

- The first ninety seconds carry the score. Proof comes before architecture, never after.

- Learning is an explicit judging criterion, so say what fought back, not what went smoothly.

- Do not claim anything the repository cannot back up. If a piece is unfinished, say so in one sentence — a working seventy percent presented honestly outscores a broken hundred percent.

### B2. Landing page and rename

The product is renamed Merge Lab. Update the name across the UI, README and page titles; do not rename packages or the npm scope, which is churn with no payoff.

- Single marketing page at "/", the existing board at "/board". No authentication, no signup, no workspace list — none of that exists in the product and must not be implied anywhere on the page.

- Sections: hero, the problem, how it works in three steps, four numbered capabilities, the six rules with their real reason strings, true numbers only, built-on-AWS, and a closing call to action.

- Restyle the board to share the landing page’s type scale, palette and borders. Visual pass only — do not touch board logic, the poll, demo mode or data assembly.

- Motion: subtle scroll reveals, a lerping custom cursor, and one small WebGL particle field in the hero. All of it disabled under prefers-reduced-motion and on screens under 768 pixels.

Hard rule: no fabricated testimonials, customer logos, compliance badges, pricing tiers or statistics. Every number on the page must be true of the repository as it stands. A judge who checks must find it accurate.

### B3. Builder Center blog post

- Top five blogs win a prize and almost nobody writes one, so the expected value here is unusually high for an hour of work.

- Best subject: hook contracts across Claude Code, Codex and Antigravity, and the constraint that injected context must be phrased as factual statements rather than instructions, because text framed as an out-of-band command trips the model’s prompt-injection defences and is surfaced to the user instead of being used.

- Link the post in the submission.

### B4. Submission verification

Confirm each of these personally. Do not assume.

☐   University enrollment verified on AWS Builder Center — nothing is scored without this

☐   The $100 team credits form has been claimed

☐   The deployed URL is live and reachable from a machine outside the team

☐   The three-minute video is uploaded and plays from a fresh browser session

☐   The repository is public and the README renders correctly on GitHub

☐   The Builder Center blog post is published and linked

# 6. Risks

| Risk | Severity | What to do |
| --- | --- | --- |
| Nothing has run on AWS. The handler path convention is an unverified guess and credentials were only recently configured. | Critical | Aryan deploys first, before anything else. Everyone else works on items that do not depend on it. |
| The four-hop path (CLI to ingest to context to hook) has never run against real infrastructure. | Critical | Prove it with one declaration before the rehearsal starts. |
| No demo repository, no rehearsal, no video. | Critical | Person A starts the demo repository now; it is blocked by nothing. |
| The demo may be read as "another AI memory tool", a crowded category. | High | Lead with the controlled experiment and the word linter. Never say "context layer" on camera. |
| A false-positive block makes the tool look hostile. | Medium | Default mode is warn. Block mode is enabled only for the demo repository. |
| Adoption: every teammate must run the CLI for the registry to be complete. | Medium | Out of scope this weekend. If asked, answer honestly: coverage degrades gracefully and absence is reported explicitly rather than implied. |
| A funded company and several open-source projects occupy the adjacent space. | Medium | Acknowledge it directly. The defensible ground is pre-push, cross-machine and enforcement-first, which none of them do. |

# 7. How to judge whether today went well

Not by how much was built. By whether a stranger can watch three minutes of video, understand the problem, see it solved twice under controlled conditions, and open a working URL afterwards.

If it comes to a choice between one more feature and one more rehearsal pass, take the rehearsal every time. A judge cannot score something they never saw.